## Hoja1
ARTEIN / INNODITEC / 3A |  |  |  | DOCUMENT TITLE |  |  |  | PURCHASE ORDER DATE | CONTRACT DATE |  | Next deadline
A |  |  |  | DOCUMENTS CODIFICATION |  |  |  | 2020-12-10 | 2020-12-11
#REF!
PROJECT NUMBER | [7 empty] | REVISION | PROVIDED DOCUMENTS / TOTAL DOCUMENTS
NNN.AA | [7 empty] | #REF! | 1
[6 empty] | CODE | DOCUMENT TITLE |  | To Delivery | Delivered | Expected Delivery date | COMMENTS
ISSSUER | PROJECT Nº | AREA | DISCIP | FAMILY | NUMBER
SSSS | NNNNNN | AA | BBB | CC | YYYY
DATE OF PURCHASE ORDER | [10 empty] | 2020-02-12
01 - SCHEDULE AND MONTHLY REPORT
DPR PROJECT DIRECTION
A | NNN.AA | PM | DPR | ISC | 01 | A-NNN.AA-PM-DPR-ISC-01 | INITIAL PROJECT SCHEDULE |  | N | - | 2020-02-19 | Engineering, purchasing, manufacturing, transport and erection schedule
A | NNN.AA | PM | DPR | GC | 01 | A-NNN.AA-PM-DPR-GC-01 | GANT CHART
A | NNN.AA | PM | DPR | FPS | 01 | A-NNN.AA-PM-DPR-FPS-01 | FINAL PROJECT SCHEDULE
A | NNN.AA | PM | DPR | CdC | 01 | A-NNN.AA-PM-DPR-CdC-01 | COST MANAGEMENT
A | NNN.AA | PM | DPR | MPR | 01 | A-NNN.AA-PM-DPR-MPR-01 | MONTHLY PROGRESS REPORT |  | N | - | Monthly | Monthly (25th of each month)
02 - ENGINEERING
DPR
A | NNN.AA | E | DPR | LT | 01 | A-NNN.AA-E-DPR-LT-01 | DOCUMENT LIST |  | Y | I | 2020-02-19
MECHANICAL
A | NNN.AA | E | MEC | TD | 01 | A-NNN.AA-E-MEC-TD-01 | GENERAL ARRANGEMENT DRAWING SERVICE AND FIRE FIGHTING WATER TANK |  | Y | I | 2020-02-28
A | NNN.AA | E | MEC | RD | 01 | A-NNN.AA-E-MEC-RD-01 | TANK ROOF DRAWING SERVICE AND FIRE FIGHTING WATER TANK 00GAD10BB001 |  | Y | I | 2020-03-11
A | NNN.AA | E | MEC | AD | 01 | A-NNN.AA-E-MEC-AD-01 | LADDERS AND STAIRS DRAWINGS |  | Y | I | 2020-03-11
A | NNN.AA | E | MEC | ND | 01 | A-NNN.AA-E-MEC-ND-01 | NOZZLES DRAWING |  | Y | I | 2020-03-11
A | NNN.AA | E | MEC | RSD | 01 | A-NNN.AA-E-MEC-RSD-01 | ROOF STRUCTURAL DESIGN |  | Y | I | 2020-02-28
A | NNN.AA | E | MEC | TSD | 01 | A-NNN.AA-E-MEC-TSD-01 | TANK STRUCTURAL DESIGN |  | Y | I | 2020-02-28
A | NNN.AA | E | MEC | DS | 01 | A-NNN.AA-E-MEC-DS-01 | TANK AND ANCILLARY DATA SHEETS |  | Y | I | 2020-02-19
INSTRUMENTATION
A | NNN.AA | E | INS | HD | 01 | A-NNN.AA-E-INS-HD-01 | DATA SHEET LEVEL INDICATOR FOR SERVICE AND FIRE FIGHTING WATER TANK 00GAD10BB001 |  | Y | I | 1900-01-27
A | NNN.AA | E | INS | AD | 01 | A-NNN.AA-E-INS-AD-01 | ASSEMBLY DRAWINGS |  | Y | I | 1900-01-27
A | NNN.AA | E | INS | IM | 01 | A-NNN.AA-E-INS-IM-01 | INSTALLATION MANUAL |  | Y | I | 2020-03-11
A | NNN.AA | E | INS | FDS | 01 | A-NNN.AA-E-INS-FDS-01 | FINAL DATA SHEETS |  | Y | I | 1900-01-27
CIVIL
A | NNN.AA | E | CIV | FD | 01 | A-NNN.AA-E-CIV-FD-01 | FOUNDATION DRAWINGS |  | Y | I | 2020-02-28
A | NNN.AA | E | CIV | FSD | 01 | A-NNN.AA-E-CIV-FSD-01 | FOUNDATIONS STRUCTURAL DESIGN |  | Y | I | 2020-02-28
OPERATION & MAINTENANCE
A | NNN.AA | E | OM | SL | 01 | A-NNN.AA-E-OM-SL-01 | COMMISSIONING AND START-UP SPARE PARTS LIST |  | Y | I | 2020-03-25
A | NNN.AA | E | OM | SL2 | 01 | A-NNN.AA-E-OM-SL2-01 | SPARE PARTS LIST FOR TWO YEARS OPERATION |  | Y | I | 2020-03-25
A | NNN.AA | E | OM | OMN | 01 | A-NNN.AA-E-OM-OMN-01 | OPERATION AND MAINTENANCE MANUAL |  | Y | C | 2020-04-10 | Including bolt tigthing porcedure
FINAL DOSSIER
A | NNN.AA | E | MEC | DO | 01 | A-NNN.AA-E-MEC-DO-01 | ENGINEERING FINAL DOSSIER SERVICE AND FIRE FIGHTING WATER TANK 00GAD10BB001 |  | Y | I | 2 WEEKS AFTER DELIVERY
03 - LOGISTIC
MATERIAL
A | NNN.AA | L | MAT | PL | 01 | A-NNN.AA-L-MAT-PL-01 | PACKING LIST |  | Y | I | 3 WEEKS AFTER PO
A | NNN.AA | L | MAT | PI | 01 | A-NNN.AA-L-MAT-PI-01 | PROFORMA INVOICE |  | Y | C | 2 WEEKS AFTER PO
A | NNN.AA | L | MAT | DGN | 01 | A-NNN.AA-L-MAT-DGN-01 | DANGEROUS GOODS NOTE |  | Y | C | 4 WEEKS AFTER PO
A | NNN.AA | L | QAC | PO | 01 | A-NNN.AA-L-QAC-PO-01 | DIMENSIONAL CONTROL PROCEDURE |  | N | - | 3 WEEKS AFTER PO
A | NNN.AA | L | INS | PO | 01 | A-NNN.AA-L-INS-PO-01 | BOLTING TORQUE PROCEDURE |  | N | - | 4 WEEKS AFTER PO
A | NNN.AA | L | MAN | SPP | 01 | A-NNN.AA-L-MAN-SPP-01 | SURFACE PREPARATION PROCEDURE |  | N | - | 4 WEEKS AFTER PO
A | NNN.AA | L | QAC | PO | 01 | A-NNN.AA-L-QAC-PO-01 | PACKING AND TRANSPORTATION PROCEDURE |  | N | - | 5 WEEKS AFTER PO | At least 1 month before the first shipment
A | NNN.AA | L | INS | HTP | 01 | A-NNN.AA-L-INS-HTP-01 | HYDRAULIC TEST PROCEDURE |  | Y | I | AT DELIVERY
A | NNN.AA | L | QAC | PO | 01 | A-NNN.AA-L-QAC-PO-01 | WELDING BOOK ( WPS, PQR , WPQR , WELDING MAP ) |  | Y | I | 3 WEEKS AFTER PO
A | NNN.AA | L | MAN | MTC | 01 | A-NNN.AA-L-MAN-MTC-01 | MATERIAL TEST AND CERTIFICATES |  | N | - | AT DELIVERY
A | NNN.AA | L | QAC | PO | 01 | A-NNN.AA-L-QAC-PO-01 | DIMENSIONAL CONTROL PROCEDURE |  | N | - | 3 WEEKS AFTER PO
04 - QUALITY
GENERAL
A | NNN.AA | Q | QAC | MN | 01 | A-NNN.AA-Q-QAC-MN-01 | QUALITY PLAN FOR BOLTED TANKS |  | Y | I | 3 WEEKS AFTER PO
A | NNN.AA | Q | MAN | ITP | 01 | A-NNN.AA-Q-MAN-ITP-01 | INSPECTION AND TEST PLAN |  | Y | C | 2 WEEKS AFTER PO
A | NNN.AA | Q | QAC | PL | 01 | A-NNN.AA-Q-QAC-PL-01 | ITP INSPECTION TEST PLAN SERVICE AND FIRE FIGHTING WATER TANK 00GAD10BB001 ERECTION |  | Y | C | 4 WEEKS AFTER PO
A | NNN.AA | Q | QAC | PO | 01 | A-NNN.AA-Q-QAC-PO-01 | DIMENSIONAL CONTROL PROCEDURE |  | N | - | 3 WEEKS AFTER PO
A | NNN.AA | Q | INS | PO | 01 | A-NNN.AA-Q-INS-PO-01 | BOLTING TORQUE PROCEDURE |  | N | - | 4 WEEKS AFTER PO
A | NNN.AA | Q | MAN | SPP | 01 | A-NNN.AA-Q-MAN-SPP-01 | SURFACE PREPARATION PROCEDURE |  | N | - | 4 WEEKS AFTER PO
A | NNN.AA | Q | QAC | PO | 01 | A-NNN.AA-Q-QAC-PO-01 | PACKING AND TRANSPORTATION PROCEDURE |  | N | - | 5 WEEKS AFTER PO | At least 1 month before the first shipment
A | NNN.AA | Q | INS | HTP | 01 | A-NNN.AA-Q-INS-HTP-01 | HYDRAULIC TEST PROCEDURE |  | Y | I | AT DELIVERY
A | NNN.AA | Q | QAC | PO | 01 | A-NNN.AA-Q-QAC-PO-01 | WELDING BOOK ( WPS, PQR , WPQR , WELDING MAP ) |  | Y | I | 3 WEEKS AFTER PO
A | NNN.AA | Q | MAN | MTC | 01 | A-NNN.AA-Q-MAN-MTC-01 | MATERIAL TEST AND CERTIFICATES |  | N | - | AT DELIVERY
A | NNN.AA | Q | QAC | PO | 01 | A-NNN.AA-Q-QAC-PO-01 | DIMENSIONAL CONTROL PROCEDURE |  | N | - | 3 WEEKS AFTER PO
FINAL DOSSIER
A | NNN.AA | Q | QAC | DO | 01 | A-NNN.AA-Q-QAC-DO-01 | END OF MANUFACTURING REPORT ( EOMR ) SERVICE AND FIRE FIGHTING WATER TANK 00GAD10BB001 |  | Y | C | 2 WEEKS AFTER DELIVERY
A | NNN.AA | Q | QAC | DO | 01 | A-NNN.AA-Q-QAC-DO-01 | MECHANICAL COMPLETION DOSSIER ( MCF) SERVICE AND FIRE FIGHTING WATER TANK 00GAD10BB002 |  | Y | C | 2 WEEKS AFTER ERECTION COMPLETION

## Hoja2
SC | Schedule
PR | Progress Report
TD | Tank drawing
RD | Roof drawing
CD | Connections drawing